## Worksheet
Task | Start Date | End Date | Responsible Party | Risk Level | Mitigation Strategy
Risk Assessment Planning | 2024-03-01 | 2024-03-15 | Project Manager | Medium | Conduct stakeholder interviews and use risk matrix.
Identify Key Risks | 2024-03-16 | 2024-03-31 | Risk Analysts | High | Use historical data and SWOT analysis.
Develop Risk Response Plan | 2024-04-01 | 2024-04-15 | Project Team | Medium | Assign owners, define thresholds and triggers.
Monitor and Review Risks | 2024-04-16 | 2024-06-30 | Project Office | Low to Medium | Hold weekly risk review meetings and update dashboard.
Contingency Planning | 2024-05-01 | 2024-05-31 | Operations Lead | High | Establish backup processes and emergency contacts.