## Worksheet
Task | Responsible Party | Start Date | End Date | Status | Risk Level | Mitigation Plan
Project Initiation & Scoping | Project Sponsor | 2024-03-01 | 2024-03-15 | On Track | Low | Conduct stakeholder workshops to validate scope.
Risk Identification Workshop | Risk Management Team | 2024-03-16 | 2024-03-20 | In Progress | Medium | Document risks using SWOT and checklists.
Risk Assessment & Prioritization | Risk Analyst | 2024-03-21 | 2024-03-25 | Pending | High | Quantify impact and likelihood using a 5x5 matrix.
Risk Response Planning | Project Manager | 2024-03-26 | 2024-04-05 | Not Started | Medium | Develop contingency and avoidance strategies.
Risk Monitoring & Review Meetings | Project Team | 2024-04-06 | 2024-06-30 | Scheduled | Low | Monthly reviews with updated risk register.