## Worksheet
Quarter | Risk Identification | Risk Assessment | Mitigation Plan | Responsibility | Timeline (MM/YYYY) | Status
Q1 | Technical debt in legacy systems | High impact, medium likelihood | Refactor key modules; allocate dev resources | Project Manager & Dev Lead | 01/2024 – 03/2024 | Pending Review
Q1 | Stakeholder resistance to change | Medium impact, high likelihood | Conduct change readiness workshops | Change Manager & Communications Lead | 01/2024 – 03/2024 | In Progress
Q2 | Data integration failures | High impact, medium likelihood | Implement automated validation scripts | IT Architect & Data Engineer | 04/2024 – 06/2024 | Planned
Q2 | Third-party vendor delays | <Medium impact, high likelihood | Negotiate SLAs and backup vendors | Procurement Lead & Project Manager | 04/2024 – 06/2024 | Under Review
Q3 | Resource constraints during rollout | Medium impact, medium likelihood | Adjust staffing plan and hire temporary staff | HR & Project Manager | 07/2024 – 09/2024 | Pending Approval
Q3 | Security breach vulnerability | High impact, high likelihood | Conduct penetration testing & patch updates | CISO & Security Team | 07/2024 – 09/2024 | Urgent Action Required
Q4 | Compliance audit failure risk | High impact, medium likelihood | Update documentation and conduct mock audits | Compliance Officer & Legal Team | 10/2024 – 12/2024 | Pending Plan Approval
Q4 | Scope creep post-launch | Medium impact, high likelihood | Implement change control board process | Project Manager & Steering Committee | 10/2024 – 12/2024 | On Track