## Worksheet
Task | Start Date | End Date | Responsible Party | Risk Level | Mitigation Strategy
Risk Identification Workshop | 2024-03-01 | 2024-03-05 | Project Manager & Risk Officer | High | Conduct cross-functional sessions with stakeholders to identify potential risks.
Risk Assessment & Prioritization | 2024-03-06 | 2024-03-10 | Risk Analyst Team | Medium | Apply qualitative and quantitative methods to assess likelihood and impact.
Develop Risk Response Plan | 2024-03-11 | 2024-03-15 | Project Steering Committee | High | Define mitigation, transfer, avoid, and accept strategies for top risks.
Risk Monitoring & Review Meetings | 2024-03-16 | 2024-06-30 | Project Manager Weekly | Ongoing | Hold bi-weekly reviews to track risk status and update response plans.
Contingency Planning & Business Impact Analysis | 2024-04-01 | 2024-05-15 | Business Unit Heads | Critical | Assess impact of major risks on operations and develop recovery plans.