## Worksheet
Task | Owner | Start Date | End Date | Risk Level | Mitigation Strategy
Project Initiation | John Smith | 2024-03-01 | 2024-03-15 | Low | Conduct stakeholder interviews and risk assessment workshops.
Scope Definition | Lisa Chen | 2024-03-16 | 2024-04-05 | Medium | Use stakeholder feedback to finalize scope; document assumptions and constraints.
Risk Identification Workshop | Mike Rivera | 2024-04-06 | 2024-04-10 | High | Hold team session to identify potential risks; use checklists and SWOT analysis.
Risk Assessment & Prioritization | Sarah Kim | 2024-04-11 | 2024-04-18 | Medium | Rate likelihood and impact; use a risk matrix to prioritize actions.
Risk Response Planning | Team Lead | 2024-04-19 | 2024-05-03 | Medium-High | Develop contingency plans for top 3 risks; assign owners and deadlines.
Monitoring & Review Meetings | John Smith | 2024-05-04 | Ongoing | Low | Hold bi-weekly meetings to review risk status and update mitigation actions.