## Worksheet
Task | Start Date | End Date | Responsible Party | Risk Level | Mitigation Strategy | Status
Project Initiation & Stakeholder Alignment | 2024-03-01 | 2024-03-15 | Project Manager | Low | Stakeholder workshops and communication plan review | On Track
Risk Assessment & Gap Analysis | 2024-03-16 | 2024-04-05 | Risk Officer | Medium | Conduct SWOT and scenario analysis; document risks in risk register | In Progress
Risk Prioritization & Action Planning | 2024-04-06 | 2024-04-20 | Project Manager & Risk Officer | High | Assign mitigation owners; define early warning signs and response protocols | Planned
Monitoring & Early Warning System Setup | 2024-04-21 | 2024-05-15 | Operations Team | Medium | Implement KPIs and dashboards for real-time risk tracking | Scheduled
Quarterly Risk Review & Update | 2024-06-01 | 2024-06-30 | Steering Committee | Medium | Review updated risk register and adjust plans as needed | Planned