## Worksheet
Task | Start Date | End Date | Responsible Team | Risk Level | Mitigation Plan | Status
Risk Identification Workshop | 2024-03-01 | 2024-03-05 | Project Team | High | Conduct stakeholder interviews and use risk matrix. | In Progress
Risk Assessment & Prioritization | 2024-03-06 | 2024-03-10 | Risk Analysts | Medium | Apply quantitative and qualitative scoring models. | Planned
Develop Risk Response Strategies | 2024-03-11 | 2024-03-18 | Project Management Office | High | Create contingency plans and assign owners. | Scheduled
Monitor & Review Risks Weekly | 2024-03-19 | Ongoing | All Teams | Medium | Hold weekly risk review meetings and update dashboard. | Active