## Worksheet
Task | Start Date | End Date | Responsible Person | Risk Level | Mitigation Strategy | Status
Risk Identification Workshop | 2024-03-01 | 2024-03-05 | John Doe | High | Conduct cross-functional sessions with stakeholders. | Completed
Threat & Vulnerability Assessment | 2024-03-06 | 2024-03-15 | Jane Smith | Medium | Perform technical analysis and audit reviews. | In Progress
Risk Register Development | 2024-03-16 | 2024-03-25 | Alex Brown | High | Document all risks with likelihood and impact. | Planned
Contingency Planning | 2024-04-01 | 2024-04-15 | Sarah Lee | Critical | Establish backup procedures and escalation paths. | Not Started
Periodic Risk Review Meetings | 2024-04-16 | 2024-12-31 | Project Steering Committee | Medium | Quarterly reviews with updates to risk register. | Scheduled
Template Version ¦ Purpose: Risk Management ¦ Template Type: Project Timeline