## Worksheet
Task | Start Date | End Date | Responsible Person | Risk Level | Status | Actions Taken
Risk Assessment Planning | 2024-03-01 | 2024-03-15 | Jane Doe | Medium | On Track | Initial risk identification completed.
Identify Key Stakeholders | 2024-03-16 | 2024-03-25 | John Smith | Low | In Progress | Stakeholder list finalized.
Conduct Risk Analysis Workshop | 2024-03-26 | 2024-04-05 | Sarah Lee | High | Pending | Workshop scheduled; materials in preparation.
Develop Risk Mitigation Plan | 2024-04-06 | 2024-04-18 | Mike Johnson | Medium | Not Started | Draft plan under review.
Monitor and Review Risks Weekly | 2024-04-19 | Ongoing | Team Lead | Low | On Track | Weekly status reports generated.