## Worksheet
Project Timeline - Weekly Risk Management
Week | Start Date | End Date | Risk Identification Activities | Risk Assessment Methodology | Risk Mitigation Actions th> | Owner Responsibility th> | Status (Green/Yellow/Red) th>
Week 1 | 2024-04-01 | 2024-04-07 | Conduct stakeholder interviews; initial risk register setup. | Qualitative analysis using risk matrix (Likelihood x Impact). | Define key risks; assign initial mitigation plans. | Jane Doe (Risk Manager) | Green
Week 2 | 2024-04-08 | 2024-04-14 | Analyze project scope for potential gaps; document dependencies. | Qualitative risk assessment with team input. | Develop contingency plans for high-risk areas. | John Smith (Project Lead) | Green
Week 3 | 2024-04-15 | 2024-04-21 | Evaluate external threats (e.g., market, regulatory). | Use SWOT analysis and scenario planning. | Update risk register with new findings; escalate critical risks. | Anna Lee (Compliance Officer) | Yellow
Week 4 | 2024-04-22 | 2024-04-28 | Conduct risk review meeting with cross-functional team. | Prioritize risks using risk score thresholds. | Implement real-time monitoring for top 5 risks. | Marcus Brown (Operations Head) | Red
Week 5 | 2024-04-29 | 2024-05-05 | Review impact of recent changes to project scope. | Re-run risk assessment with updated parameters. | Adjust mitigation plans and update communication plan. | Jane Doe (Risk Manager) | Green