## Worksheet
Project Name | Risk ID | Risk Description | Probability | Impact | Risk Score (P×I) | Risk Category | Owner | Mitigation Strategy | Status | Last Reviewed | Action Plan
Smart City Infrastructure Project | R-001 | Power outage during peak hours due to aging grid infrastructure. | High | High | 9 | Technical | Dr. Alan Reed | Upgrade substations and deploy microgrid backups. | Active | 2024-03-15 | Complete grid audit by Q2.
AI-Based Healthcare Platform | R-002 | Data breach due to unencrypted patient records. | Medium | High | 6 | Security | Ms. Lena Patel | Implement end-to-end encryption and access controls. | Pending Review | 2024-03-20 | Schedule penetration testing by April.
Renewable Energy Expansion | R-003 | Supply chain delays for solar panel components. | Low | Medium | 3 | Supply Chain | Mr. James Kim | Diversify suppliers and pre-order critical components. | Planned | 2024-03-25 | Identify alternative suppliers by April.
Cloud Migration Initiative | R-004 | Service downtime during migration window. | High | Medium | 6 | Operational | Eng. Sofia Chen | Conduct phased rollout with rollback procedures. | In Progress | 2024-03-30 | Complete Phase 1 by April 5.
Customer Experience Platform Launch | R-005 | Negative user feedback due to poor interface design. | Medium | High | 6 | User Experience | Ms. Naomi White | Conduct usability testing and redesign key flows. | On Hold | 2024-04-05 | Usability study scheduled for April 8.