## Worksheet
Project Name | Project ID | Start Date | End Date | Risk Level | Likelihood | Impact | Risk Description | Mitigation Strategy | Owner | Status
Digital Transformation Initiative | DTI-2024-001 | 2024-03-15 | 2025-06-30 | High | Medium | Critical | Failure of third-party integration may delay delivery. | Implement fallback systems and conduct pre-integration testing. | Sarah Chen | Active
Cloud Migration Project | CM-2024-002 | 2024-05-01 | 2024-11-30 | Medium | High | High | Data loss during migration due to configuration errors. | Backup all data and perform full validation post-migration. | James Rivera | On Track
Customer Portal Redesign | CP-2024-003 | 2024-06-10 | 2024-12-31 | Low | Medium | Moderate | Increased user confusion due to interface changes. | Conduct user testing and include tooltips and guided onboarding. | Maria Lopez | Planning