## Worksheet
Project Name | Risk ID | Risk Description | Likelihood | Impact th> | Priority | Owner | Status | Mitigation Plan | Last Reviewed
Website Redesign | R-001 | High traffic during launch may overwhelm server capacity. | High | Medium | Medium | John Smith | Active | Scale servers dynamically using auto-scaling groups. | 2024-03-15
Mobile App Launch | R-002 | Users may face crashes due to outdated device compatibility. | Medium | High | <High | Sarah Lee | Pending Review | Update app to support latest OS versions; conduct compatibility testing. | 2024-03-10
Data Migration Project | R-003 | Loss of data integrity during transfer process. | High | High | <Critical | Mike Chen | In Progress | Use checksum verification and backup during transfer. | 2024-03-12
Cloud Infrastructure Upgrade | R-004 | Service outages due to configuration errors during deployment. | Medium | High | High | Lisa Wong | Planned | Deploy in phased batches with rollback plan. | 2024-04-01