## Worksheet
Project Name | Risk Level | Risk Description | Likelihood | Impact th> | Mitigation Strategy | Owner | Status | Last Updated
Phase 1 Development | High | Critical dependency on external vendor delivery. | Medium | High | Dual sourcing of vendor; establish clear SLAs and contingency plan. | Alex Morgan | Active | 2024-03-15
User Training Program | Medium | Low participation due to scheduling conflicts. | Low | Medium | Flexible scheduling and virtual training sessions. | Jamie Lee | On Hold | 2024-03-10
System Integration | High | Compatibility issues between legacy and new systems. | High | Critical | Conduct thorough API testing; implement fallback protocols. | Ryan Patel | In Progress | 2024-03-14
Data Migration | Medium | Risk of data corruption during transfer. | Medium | High | Validate data in stages; backup prior to migration. | Sophia Chen | Planned | 2024-04-01