## Worksheet
Project Name | Project ID | Start Date | End Date | Risk Level | Risk Description | Likelihood | Impact | Owner | Mitigation Strategy | Monitoring Frequency | Status
Website Redesign | PJ-2024-001 | 2024-03-15 | 2024-06-30 | High | Third-party vendor delay in content delivery | Medium | High | Sarah Chen | Contingency budget allocation and alternate vendor onboarding | Monthly review + bi-weekly check-ins | Active
Cloud Migration | PJ-2024-002 | 2024-04-01 | 2024-08-31 | Moderate | Data loss during transfer process | High | Medium | David Kim | Implement data validation scripts and backups during migration | Weekly audit | Planned
Customer Portal Launch | PJ-2024-003 | 2024-05-10 | 2024-11-15 | Low | User interface usability issues | Medium | Low | Lisa Patel | Conduct UX testing with sample users before launch | Bi-weekly usability reviews | On Track