## Worksheet
Project Name | Risk ID | Risk Description | Likelihood | Impact th> | Risk Priority | Owner | Mitigation Plan | Status | Date Identified | Next Review Date
Website Redesign | R-001 | Loss of user data due to insecure form handling. | High | Critical | High | Jane Doe | Implement encryption for all form inputs and conduct third-party security audit. | Active | 2024-03-15 | 2024-06-15
Mobile App Launch | R-002 | App crashes on low-end devices. | Medium | High | Medium | John Smith | Optimize code for performance and conduct device testing on 5+ platforms. | Pending Review | 2024-03-20 | 2024-05-20
Client Onboarding System | R-003 | Delayed onboarding due to poor user interface. | Low | Medium | Low | Alex Chen | Redesign UI for simplicity and add tooltips for new users. | In Progress | 2024-03-18 | 2024-04-18