## Worksheet
Project Name | Risk ID | Risk Description | Likelihood | Impact th> | Priority Level | Mitigation Strategy | Responsible Person | Last Reviewed Date | Status
Website Redesign | R-001 | User data exposure during migration phase. | Medium | High | High | Implement encryption and access controls during transfer. | Sarah Chen | 2024-03-15 | Active
Mobile App Launch | R-002 | Third-party API failure leading to service outage. | High | Medium | <Medium | Set up fallback mechanisms and load balancing. | James Reed | 2024-03-10 | Monitoring
Cloud Migration | R-003 | Data loss due to improper backup procedures. | Medium | Critical | High | Automate backups and validate retention policies. | Lisa Park | 2024-03-05 | Planned
Internal Audit Process | R-004 | Unauthorized access to audit logs. | Low | High | Medium | Restrict log access to authorized personnel only. | Michael Torres | 2024-03-01 | Completed