## Worksheet
Project Name | Project Manager | Start Date | End Date | Risk Level | Risk Description | Likelihood | Impact | Mitigation Strategy | Owner | Status | Last Updated
Digital Transformation Initiative | Sarah Johnson | 2024-03-01 | 2025-06-30 | High | Data breach due to legacy system vulnerabilities. | Medium | Critical | Implement multi-factor authentication and conduct quarterly penetration testing. | IT Security Team | Active | 2024-04-15
Cloud Migration Project | Michael Chen | 2024-05-01 | 2024-10-31 | Medium | Service downtime during migration window. | High | High | Perform phased rollout with backup systems and real-time monitoring. | DevOps Team | On Track | 2024-06-10
Global Expansion Program | Linda Patel | 2024-07-01 | 2025-12-31 | High | Cultural resistance in new markets. | Medium | Moderate | Launch localized training and engagement programs with local leaders. | HR & Global Operations | Planning Phase | 2024-07-15
AI Integration in Customer Service | David Kim | 2024-08-01 | 2025-03-31 | Medium | Loss of customer trust due to inaccurate AI responses. | High | Moderate | Establish clear response protocols and human oversight layer. | Customer Experience Team | In Review | 2024-08-20