## Worksheet
Project Name | Risk ID | Risk Description | Likelihood | Impact(th) | Risk Level | Owner | Mitigation Strategy | Status | Last Updated
Digital Transformation Initiative | RISK-001 | Failure to integrate legacy systems with new platform. | High | Critical | Critical | Jane Smith | Conduct phased integration with backup protocols. | Active | 2024-03-15
Cloud Migration Project | RISK-002 | Data loss during migration process. | Medium | High | <High | Mike Johnson | Implement automated backups and checksum validation. | Planning | 2024-03-10
Customer Portal Upgrade | RISK-003 | Poor user adoption due to complex interface. | Low | Medium | Moderate | Sarah Lee | Conduct usability testing and simplify navigation. | Review | 2024-03-08
AI Analytics Deployment | RISK-004 | Model bias leading to inaccurate predictions. | High | Critical | Critical | David Kim | Audit training data and implement bias detection tools. | Pending Review | 2024-03-12