## Worksheet
Project Name | Risk ID | Risk Description | Probability | Impact th> | Likelihood x Impact (Score) | Risk Category | Owner | Mitigation Strategy | Status | Last Updated
Website Redesign Project | RISK-2024-001 | Failure to meet launch deadline due to delayed developer feedback. | Medium | High | 6 | Technical | Jane Doe | Implement weekly sprint reviews and automated build checks. | Active | 2024-04-15
Cloud Migration Initiative | RISK-2024-002 | Data loss during migration process due to configuration errors. | High | Critical | 12 | Operational | John Smith | Conduct full data validation and backup pre-migration. | In Progress | 2024-04-10
Mobile App Launch | RISK-2024-003 | User authentication failure due to third-party API downtime. | Medium | High | 6 | Security | Alex Chen | Implement fallback authentication and API redundancy. | Planned | 2024-05-01