## Worksheet
Risk ID | Risk Description | Category | Likelihood | Impact | Risk Score | Ownership | Mitigation Strategy | Response Plan | Status | Last Updated
R-001 | Failure of critical server backup system | Operational | High | High | 9 | IT Infrastructure Team | Implement redundant backup systems with automated failover | Daily monitoring and alerts; immediate restoration if failure detected | Active | 2024-04-05
R-002 | Data breach due to outdated software | Security | Medium | High | 7 | Cybersecurity Team | Patch all systems quarterly; conduct penetration testing biannually | Isolate affected systems and notify stakeholders within 30 minutes | Monitoring | 2024-03-28
R-003 | Project scope creep due to stakeholder demands | Project Management | High | Medium | 8 | Project Manager | Enforce change control process and require formal approvals | Review scope changes in weekly steering committee meetings | Active | 2024-04-03
R-004 | Supply chain delay due to vendor issues | Logistics | Medium | High | 6 | Procurement Team | Identify alternative vendors and build buffer inventory | Activate backup vendor within 48 hours of delay notification | Pending | 2024-04-01
R-005 | Regulatory non-compliance in data handling | Compliance | Low | High | 4 | Legal & Compliance Officer | Conduct compliance audits quarterly and update policies | Immediate audit upon detection; corrective actions within one week | Under Review | 2024-03-30