## Worksheet
Project Name | Risk ID | Risk Description | Likelihood | Impact | Priority Level | Owner | Mitigation Plan | Status | Last Updated
Website Redesign Launch | RISK-001 | High user drop-off during checkout process. | Medium | High | Critical | Sarah Johnson | Improve form validation and add progress indicators. | Active | 2024-04-15
Mobile App Integration | RISK-002 | Third-party API may experience downtime. | High | <Medium | High | James Wilson | Implement fallback mechanism and cache data. | Planned | 2024-04-18
Cloud Migration Project | RISK-003 | Data loss during migration process. | Low | Critical | Critical | Lisa Chen | Perform full backup and validate data integrity post-migration. | Pending | 2024-04-10