## Worksheet
Project Name | Project ID | Start Date | End Date | Risk Category | Risk Description | Likelihood | Impact | Risk Score | Mitigation Strategy | Owner | Status
New Customer Onboarding System | PRJ-001 | 2024-03-01 | 2024-06-30 | Security | Unauthorized access to user data during onboarding. | Medium | High | 7 | Implement multi-factor authentication and role-based access control. | Sarah Johnson | Active
Cloud Migration Initiative | PRJ-002 | 2024-04-15 | 2024-09-30 | Operational | Data loss during migration process. | High | Critical | 9 | Backup and test migration in staging environment first. | David Chen | Monitoring
Product Launch Campaign | PRJ-003 | 2024-05-05 | 2024-07-31 | Market Risk | Negative public reaction to product features. | Medium | High | 7 | Conduct pre-launch customer feedback sessions and adjust messaging. | Lisa Martinez | In Progress
Vendor Performance Review | PRJ-004 | 2024-03-30 | 2024-06-30 | Supply Chain | Vendor delay in delivery of critical components. | High | Medium | 8 | Identify alternative suppliers and negotiate service level agreements. | Mark Wilson | Review Phase