## Worksheet
Project Name | Project ID | Start Date | End Date | Risk Level | Risk Description | Mitigation Strategy | Owner | Status | Last Updated
Website Redesign | PRJ-001 | 2024-03-01 | 2024-06-30 | High | Third-party vendor delays may impact launch timeline. | Engage backup vendor; implement buffer in schedule. | Alex Rivera | On Track | 2024-04-15
Mobile App Launch | PRJ-002 | 2024-04-10 | 2024-08-31 | Medium | User data privacy compliance challenges. | Conduct additional audits; ensure regulatory alignment. | Samantha Lee | In Progress | 2024-05-03
Cloud Migration | PRJ-003 | 2024-05-05 | 2024-10-31 | High | Potential service outages during transition. | Schedule phased rollout with failover protocols. | David Chen | Planned | 2024-06-10
Customer Support System Upgrade | PRJ-004 | 2024-06-15 | 2024-09-30 | Low | Minor training gap for support staff. | Provide onboarding sessions and quick-reference guides. | Jessica Wong | Pending Review | 2024-07-05