## Worksheet
Project Name | Risk ID | Risk Description | Probability | Impact th> | Risk Level | Owner | Mitigation Strategy | Status | Last Updated
Product Launch Q3 | RK-001 | Delayed market entry due to regulatory approval delays | High | High | Critical | Sarah Johnson | Prioritize regulatory submissions; engage with compliance team early | Active | 2023-10-05
Cloud Migration Initiative | RK-002 | Data loss during migration process | Medium | High | High | Marcus Lee | Implement backup and validation checks; use phased rollout | In Progress | 2023-10-04
Customer Portal Upgrade | RK-003 | System downtime during peak usage hours | High | Medium | Moderate | Lisa Chen | Schedule maintenance off-peak; add load balancing features | Pending Review | 2023-10-03