## Worksheet
Project Name | Risk ID | Risk Description | Likelihood | Impact th> | Risk Rating | Owner | Mitigation Plan | Status | Last Updated
Phase 1 Development | R-001 | Delay in third-party integration due to API changes | Medium | High | High | Jane Smith | Engage vendor for API documentation update; create fallback logic. | Active | 2024-04-15
Market Launch Campaign | R-002 | Potential negative public reaction to new pricing model | Low | High | Moderate | Mark Johnson | Conduct customer survey; adjust messaging in pre-launch phase. | Planned | 2024-05-01
Infrastructure Upgrade | R-003 | Server overload during peak traffic hours | High | Medium | High | Alex Chen | Implement load balancing and auto-scaling; conduct stress tests. | In Progress | 2024-04-20