## Worksheet
Project Name | Team Member | Risk Identified | Likelihood | Impact th> | Risk Rating | Mitigation Strategy | Owner | Last Updated
Website Redesign Phase 1 | Sarah Chen | Poor user engagement on mobile | Medium | High | High | Optimize mobile UI, conduct user testing with real users. | Sarah Chen | 2024-04-15
AI Chatbot Launch | James Reed | Data privacy breach during testing | Low | Critical | Critical | Implement end-to-end encryption and conduct privacy audits. | James Reed | 2024-04-12
Supply Chain Optimization | Amina Patel | Supplier delays in delivery | High | Medium | Medium-High | Diversify supplier base and create buffer inventory. | Amina Patel | 2024-04-10
Cloud Migration Project | David Kim | Downtime during migration window | High | High | Critical | Perform phased migration with rollback plan and real-time monitoring. | David Kim | 2024-04-08