## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact th> | Current Status | Owner | Mitigation Strategy | Response Plan | Last Reviewed Date | Next Review Date
RM-001 | Delays in third-party vendor delivery | Supply Chain | Medium | High | Pending Assessment | Jane Smith | Establish backup vendor list and monitoring protocol. | Activate contingency plan if delivery exceeds 5 days. | 2024-03-15 | 2024-06-15
RM-002 | Inadequate cybersecurity protocols | Technology | High | Critical | Active Mitigation | Michael Johnson | Implement multi-factor authentication and regular penetration testing. | Enforce access control policies and conduct quarterly security audits. | 2024-03-10 | 2024-09-10
RM-003 | Lack of skilled workforce in key departments | Human Resources | Medium | High | Monitoring Phase | Anna Lee | Launch internal training program and external recruitment drive. | Assign mentorship roles and track skill gaps quarterly. | 2024-03-12 | 2024-07-12