## Worksheet
Project Name | Team Member | Risk Identified | Impact Level | Likelihood | Current Status | Mitigation Action | Owner | Next Review Date
Website Redesign | Alex Morgan | Server downtime during launch | High | Medium | Active | Perform load testing and deploy in staging first. | Dev Team Lead | 2023-10-15
Mobile App Launch | Jordan Lee | User data privacy breach | Critical | High | Pending Review | Conduct full audit and update encryption protocols. | Security Officer | 2023-10-10
Cloud Migration Project | Taylor Reed | Unexpected vendor cost increase | Medium | Low | Planned | Negotiate long-term contract with backup vendor. | Procurement Manager | 2023-10-25
Customer Onboarding Platform | Morgan Clark | Integration failure with CRM | High | Medium | In Progress | Develop fallback API and implement error handling. | Integration Lead | 2023-10-20