## Worksheet
Date | Risk Identified | Risk Category | Likelihood (1-5) | Impact (1-5) | Risk Score | Mitigation Strategy | Responsible Party | Due Date | Status
2024-04-01 | System Downtime | Technology | 4 | 5 | 20 | Implement redundant servers and automated failover | IT Department | 2024-04-30 | Open
2024-04-15 | Data Breach | Security | 3 | 4 | 12 | Enhance encryption and conduct regular audits | Security Team | 2024-05-15 | Planned
2024-05-01 | Regulatory Non-compliance | Compliance | 5 | 5 | 25 | Update policy documentation and schedule training | Legal & Compliance Office | 2024-06-30 | High Priority
2024-05-10 | Vendor Failure | Supply Chain | 4 | 3 | 12 | Identify and onboard backup vendors | Procurement Team | 2024-06-10 | In Progress