## Worksheet
Date | Risk Identified | Risk Level | Impact Assessment | Mitigation Strategy | Responsible Party | Status
2024-04-01 | Data Breach Risk | High | Critical to customer trust and compliance | Implement two-factor authentication and regular audits | IT Security Team | Active
2024-04-05 | Supply Chain Disruption | Moderate | May affect delivery timelines and costs | Diversify supplier base and establish backup vendors | Purchasing Manager | Planned
2024-04-10 | Regulatory Change Risk | High | Likely to require process reconfiguration | Legal and Compliance Office will review updates | Legal Team | Pending Review
2024-04-15 | Key Personnel Exit | Moderate | Potential loss of institutional knowledge | Conduct knowledge transfer sessions and document critical processes | HR & Operations Lead | On Track