## Worksheet
Date | Risk Identified | Risk Category | Likelihood (1-5) | Impact (1-5) | Current Mitigation Strategy | Residual Risk Level | Owner/Responsible Party | Last Reviewed Date | Action Plan & Timeline
2024-03-15 | System Downtime Due to Power Outage | Operational Risk | 4 | 5 | Backup generator in place; automatic failover protocol activated. | Medium | IT Operations Team | 2024-03-15 | Upgrade generator capacity by Q2; conduct biannual failover tests.
2024-04-03 | Data Breach from Third-Party Vendor | Security Risk | 3 | 4 | Vendor access limited to minimum required; encryption in transit and at rest. | Low-Medium | Security & Compliance Officer | 2024-04-03 | Conduct quarterly vendor security audits; implement multi-factor authentication for all vendor portals.
2024-05-10 | Regulatory Change in Data Privacy Law | Compliance Risk | 2 | 5 | Legal team reviewing compliance framework; internal policy updates underway. | High | Legal Department | 2024-05-10 | Finalize policy update by June 30; train staff on new compliance procedures.
2024-06-18 | Supply Chain Disruption from Geopolitical Events | External Risk | 5 | 4 | Diversified supplier base; contingency inventory maintained. | High | Procurement & Logistics Manager | 2024-06-18 | Identify secondary suppliers by Q3; monitor geopolitical indicators monthly.