## Worksheet
Date | Risk Identified | Risk Level | Likelihood | Impact | Mitigation Strategy | Responsible Person | Action Date | Status
2024-04-05 | Data Breach Due to Unsecured APIs | High | Medium | Critical | Implement API encryption and access controls | DevOps Team | 2024-05-05 | In Progress
2024-04-10 | Outage Due to Server Failure | Medium | High | Severe | Deploy redundant servers with auto-failover | Infra Team | 2024-05-10 | Planned
2024-04-15 | Third-Party Vendor Mismanagement | High | Medium | Critical | Conduct vendor audits and require SLAs | Compliance Officer | 2024-05-15 | Pending Approval
2024-04-20 | Cyberattack via Phishing | High | High | Critical | Enhance employee training and email filtering | Security Team | 2024-05-20 | Active
2024-04-25 | Regulatory Non-Compliance Risk | Medium | High | Critical | Conduct quarterly compliance reviews and update policies | Legal Team | 2024-06-05 | Scheduled