## Worksheet
Date | Risk Identified | Likelihood | Impact th> | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Action Due Date
2024-03-15 | Data Breach Due to Poor Access Controls | High | Critical | 9 | Implement MFA and role-based access controls. | IT Security Team | 2024-04-15
2024-03-20 | Supply Chain Disruption | Medium | High | 6 | Diversify suppliers and establish backup vendors. | Procurement Manager | 2024-04-30
2024-03-25 | Cyberattack via Phishing | High | Medium | 6 | Conduct phishing simulations and user training. | HR & Training Department | 2024-05-15
2024-04-01 | Key Personnel Departure | Medium | High | 6 | Develop succession plans and cross-train staff. | HR & Operations | 2024-05-01