## Worksheet
Date | Risk Identified | Likelihood | Impact | Risk Rating (Likelihood × Impact) | Mitigation Strategy | Owner | Status
2024-03-15 | System Downtime During Peak Hours | High | Medium | High | Implement automated failover and load balancing. | Raj Patel | In Progress
2024-03-18 | Data Breach Due to Poor Access Controls | Medium | High | High | Enforce role-based access and multi-factor authentication. | Sarah Kim | Pending Review
2024-03-22 | Third-Party Vendor Failure | Low | High | Moderate | Negotiate SLAs and establish backup vendors. | James Lee | Planned
2024-03-25 | Regulatory Non-Compliance Risk | High | High | Very High | Schedule quarterly audits and compliance training. | Linda Torres | Active