## Worksheet
Date | Risk Identified | Potential Impact | Likelihood | Risk Rating (1-5) | Mitigation Strategy | Owner / Team Member | Status
2024-03-15 | Data Breach Due to Unpatched System | Severe financial loss and reputational damage | High | 4 | Implement automated patch management and conduct monthly security audits | IT Security Team | Pending Review
2024-04-01 | Supply Chain Disruption | Operational downtime and cost overruns | Moderate | 3 | Establish dual supplier agreements and maintain safety stock buffers | Purchasing & Logistics Team | Active
2024-03-28 | Employee Training Gap on Compliance | Non-compliance with regulations and fines | Medium | 2 | Schedule mandatory compliance training quarterly and track participation | HR & Compliance Officer | In Progress
2024-05-10 | Third-Party Vendor Failure | Service interruption and customer dissatisfaction | High | 4 | Conduct vendor risk assessments annually and define Service Level Agreements (SLAs) | Risk Management Office | Planned