## Worksheet
Risk Identification Phase | Assessment Method | Responsible Team | Timeline (Start - End) | Risk Priority Level (1-5) | Status
Initial Survey & Stakeholder Interviews | SWOT Analysis + Expert Delphi | Project Leadership Team | 01/01/2024 - 01/31/2024 | 3 | Pending Review
Risk Categorization & Mapping | Matrix Analysis (Likelihood vs Impact) | Risk Management Office | 02/01/2024 - 02/15/2024 | 4 | In Progress
Quantitative Risk Assessment | Monte Carlo Simulation & Fault Tree Analysis | Data Science & Engineering Team | 03/01/2024 - 03/31/2024 | 5 | Scheduled
Response Strategy Development | Scenario Planning & Business Impact Analysis (BIA) | Operations & Compliance Team | 04/01/2024 - 04/30/2024 | 4 | Pending Approval
Risk Monitoring & Review Cycle | Real-Time Dashboards & Monthly Audits | Central Risk Governance Board | Ongoing (Monthly) | 2 | Active