## Worksheet
Risk Identification | Risk Description | Impact Level | Likelihood | Risk Score (Impact × Likelihood) | Mitigation Strategy | Owner | Due Date | Status
RISK-001 | System outage due to server failure | High | High | 9 | Implement redundant servers and automatic failover | IT Infrastructure Team | 2024-06-15 | In Progress
RISK-002 | Data breach from unsecured third-party access | Critical | Medium | 6 | Enforce MFA and conduct regular third-party audits | Security Operations Team | 2024-07-10 | Planned
RISK-003 | Supply chain delay due to vendor issues | Medium | High | 6 | Diversify suppliers and establish backup contracts | Procurement Department | 2024-05-30 | Completed
RISK-004 | Employee data misuse due to poor training | Medium | Low | 3 | Conduct regular compliance and data handling training | HR & Compliance Team | 2024-08-01 | Not Started