## Worksheet
Risk Identification | Risk Description | Likelihood | Impact | Risk Priority | Mitigation Strategy | Responsible Party | Due Date
RISK-001 | System downtime during peak hours | Medium | High | P2 (High Priority) | Implement redundant servers and scheduled backups | IT Department | 2024-04-15
RISK-002 | Compliance breach due to outdated policies | Low | High | P3 (Medium Priority) | Conduct policy review and update regulatory framework | Legal & Compliance Team | 2024-05-20
RISK-003 | Third-party vendor failure | <Medium | High | P2 (High Priority) | Negotiate SLAs and diversify vendor base | Procurement Team | 2024-03-30
RISK-004 | Data breach from phishing attacks | High | Very High | P1 (Critical Priority) | Deploy advanced email filtering and employee training | Cybersecurity Team | 2024-04-05