## Worksheet
Date | Risk Identified | Risk Level | Owner | Mitigation Plan | Status | Next Review Date
2024-04-01 | System outage due to server failure | High | IT Director | Implement redundant servers and automated failover | In Progress | 2024-04-08
2024-04-02 | Data breach vulnerability | Medium | Security Manager | Conduct penetration testing and update access controls | Pending Review | 2024-04-10
2024-04-03 | Third-party supplier delays | Low | Procurement Lead | Negotiate revised delivery timelines and backup suppliers | Completed | 2024-04-15
2024-04-04 | Employee data misuse risk | High | HR Director | Implement mandatory training and role-based access control | Planned | 2024-04-12
2024-04-05 | Power supply failure in data center | High | Facilities Manager | Upgrade to dual power sources with backup generators | In Planning | 2024-04-18