## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact th> | Current Status | Ownership | Mitigation Plan | Next Review Date
R-001 | System outage due to server failure | Technical | High | Critical | Active | IT Operations Team | Implement redundant servers and automated failover. | 2024-06-15
R-002 | Data breach from unpatched software | Security | Medium | High | <Active | Cybersecurity Team | Enforce patch management policy and conduct quarterly audits. | 2024-07-10
R-003 | Regulatory non-compliance due to policy gaps | Compliance | Low | High | Under Review | Legal & Compliance Office | Update internal policies and conduct compliance training. | 2024-08-01
R-004 | Supply chain disruption from vendor issues | Operational | Medium | Medium | Planned | Procurement Team | Identify alternate suppliers and build backup inventory. | 2024-09-15
R-005 | Employee data misuse due to poor access controls | Security | High | Medium | Active | HR & IT Security Team | Implement role-based access controls (RBAC) and audit logs. | 2024-06-30