## Worksheet
Risk Identification | Risk Description | Impact Level | Probability | Risk Rating (Impact × Probability) | Mitigation Strategy | Owner | Timeline (Start – End) | Status | Review Date
RISK-001 | System downtime due to server failure | High | Medium | High | Implement redundant servers with auto-failover | IT Operations Team | 2024-01-15 – 2024-06-30 | Active | 2024-11-30
RISK-002 | Data breach through phishing attack | Critical | High | Critical | Conduct employee training, deploy multi-factor authentication | Security Team | 2024-02-01 – 2024-12-31 | Planned | 2024-10-15
RISK-003 | Supply chain delay affecting delivery timelines | Medium | High | High | Diversify suppliers and maintain safety stock | Procurement Department | 2024-03-10 – 2025-03-10 | Active | 2024-12-15
RISK-004 | Regulatory non-compliance due to policy updates | High | Medium | High | Conduct quarterly compliance audits and update policies | Legal & Compliance Office | 2024-04-01 – 2025-12-31 | Monitoring | 2024-11-30
RISK-005 | Cyberattack on third-party vendor | Critical | Low | Moderate | Establish vendor security evaluation protocol | Risk Management Office | 2024-05-01 – 2024-12-31 | Pending Approval | 2024-10-30