## Worksheet
Risk Item | Risk Description | Likelihood | Impact th> | Risk Rating (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Deadline | Status | Review Date
Project Delay | Delays due to resource unavailability or scope changes. | Medium | High | Medium-High | Implement buffer timelines and regular stakeholder reviews. | Project Manager | 2024-06-30 | In Progress | 2024-05-15
Budget Overrun | Unexpected costs due to inflation or scope creep. | Low | contenteditable="true">HighHigh | Medium | Conduct monthly cost reviews and adjust forecasts. | Finance Lead | 2024-07-15 | Planned | 2024-06-01
Security Breach | Unauthorized access to sensitive data. | High | Critical | Critical | Implement multi-factor authentication and regular audits. | CISO & IT Team | 2024-08-31 | Not Started | 2024-05-30
Vendor Failure | Key vendor unable to deliver on time or at quality. | Medium | High | High | Diversify supplier base and include contingency plans. | Procurement Manager | 2024-09-15 | Planned | 2024-06-15