## Worksheet
Risk Identification | Risk Description | Likelihood | Impact | Risk Score (L×I) | Risk Category | Mitigation Strategy | Responsible Party | Timeline | Status
RISK-001 | System outage due to server failure | High | Critical | 9 | IT Infrastructure | Implement redundant servers and automated failover | IT Operations Team | Q1 2024 – Q4 2024 | Active
RISK-002 | Data breach from unsecured APIs | Medium | High | 6 | Security | Enforce API authentication and encryption | Cybersecurity Team | Ongoing | Planned
RISK-003 | Vendor delay in delivery | Low | Medium | 3 | Supply Chain | Diversify vendor base and establish buffer periods | Procurement Team | Q2 2024 | Pending Review
RISK-004 | Regulatory non-compliance | High | Critical | 9 | Compliance | Conduct regular audits and training programs | Legal & Compliance Office | Quarterly reviews | Active