## Worksheet
Date | Risk Identification | Risk Description | Likelihood | Impact> | Risk Rating (L×I) | Mitigation Strategy | Owner | Due Date | Status
01/01/2024 | Project Delay | Delays in vendor delivery may impact project timeline. | Medium | High | 6 | Establish buffer time and alternate suppliers. | Project Manager | 02/01/2024 | Pending
01/15/2024 | Budget Overrun | Unplanned costs may exceed approved budget. | Low | High | 3 | Conduct monthly cost reviews and reallocate funds. | Finance Director | 02/15/2024 | Active
02/01/2024 | Data Breach | Unauthorized access to sensitive customer data. | High | Critical | 12 | Implement multi-factor authentication and regular audits. | CISO | 03/01/2024 | Planned
03/15/2024 | Regulatory Change | Unexpected changes in compliance laws. | Medium | Medium | 6 | Monitor regulatory updates and schedule review meetings. | Legal Officer | 04/15/2024 | Monitoring