## Worksheet
Risk Identification | Risk Description | Likelihood | Impact | Risk Rating | Mitigation Strategy | Responsibility | Timeline | Status
1 | System downtime due to server failure | High | Critical | High | Implement redundant servers and automated failover | IT Operations Team | Q1 2024 – Ongoing | In Progress
2 | Data breach due to unauthorized access | Medium | High | Medium-High | Strengthen authentication and deploy multi-factor access | Security & Compliance Team | Q2 2024 | Planned
3 | Project scope creep leading to delays | High | Medium | High | Implement change control board and scope management process | Project Management Office | Ongoing | Active
4 | Regulatory non-compliance penalties | Low | Critical | Medium-Critical | Conduct regular audits and train staff on compliance policies | Legal & Compliance Team | Q4 2024 | Planned