## Worksheet
Risk Item | Risk Level | Owner | Assessment Date | Mitigation Strategy | Deadline | Status
Data Breach | High | IT Security Team | 2024-03-15 | Implement multi-factor authentication and regular audits. | 2024-06-30 | In Progress
Supply Chain Disruption | Medium | Procurement Department2024-03-10 | Diversify suppliers and establish backup vendors. | 2024-05-15 | Planned
System Downtime | High | Infrastructure Team | 2024-03-12 | Deploy redundant servers and automated failover. | 2024-07-31 | Not Started
Compliance Failure | High | Legal & Compliance Office | 2024-03-05 | Conduct mandatory training and update policies. | 2024-04-30 | On Track