## Worksheet
Risk Item | Risk Category | Likelihood | Impact> | Priority Level | Owner | Mitigation Strategy | Due Date | Status
System Downtime | Operational Risk | High | High | P1 (Critical) | IT Operations Manager | Redundant server deployment and failover testing | 2024-04-15 | In Progress
Data Breach | Security Risk | Medium | High | P2 (High) | Cybersecurity Team Lead | Implement multi-factor authentication and audit logs | 2024-05-10 | Pending Review
Supplier Delay | Supply Chain Risk | Low | Medium | P3 (Moderate) | Sourcing Coordinator | Negotiate alternative suppliers and buffer inventory | 2024-06-01 | Planned
Compliance Gap | Regulatory Risk | High | High | P1 (Critical) | Legal & Compliance Officer | Conduct internal audit and update policies | 2024-03-30 | Completed