## Worksheet
Date | Risk Item | Risk Level | Mitigation Action | Responsible Person | Due Date | Status
2024-04-05 | Data Breach Due to Unpatched Systems | High | Patch all critical systems by end of week | IT Manager | 2024-04-08 | Pending
2024-04-05 | Third-party Vendor Security Issues | Medium | Conduct security audit of all vendors | Compliance Officer | 2024-04-10 | Planned
2024-04-05 | Insider Threat from Employee Access | High | Implement role-based access controls | Security Analyst | 2024-04-09 | In Progress
2024-04-05 | Failure to Backup Critical Data | Medium | Establish daily automated backups | IT Support Lead | 2024-04-07 | Pending