## Worksheet
Risk Item | Risk Description | Likelihood | Impact | Current Controls | Risk Rating (Likelihood × Impact) | Priority Level | Mitigation Strategy | Responsible Party | Timeline | Status
Data Breach | Unauthorized access to sensitive customer or financial data. | High | Critical | Firewall, encryption, multi-factor authentication. | 8 (High) | Immediate | Implement endpoint detection and response (EDR), conduct regular penetration testing. | IT Security Team | Q1 2024 | Pending
System Downtime | Critical business systems fail due to hardware or software failure. | Medium | <> HighBackup servers, disaster recovery plan. | 6 (Medium-High) | High | Establish failover procedures and automated backups. | Infrastructure Team | Ongoing | Active
Compliance Violation | Failure to meet regulatory requirements (e.g., GDPR, HIPAA). | Low | High | Policy reviews, audit logs, training programs. | 3 (Medium) | Medium | Conduct quarterly compliance audits and update policies. | Legal & Compliance Office | Quarterly | On Track
Third-Party Vendor Risk | Vendor failure or breach due to poor security practices. | Medium | Medium | Vendor risk assessment, contract clauses, audit rights. | 4 (Medium) | Medium | Require annual security assessments and SLAs from vendors. | Risk Management Office | Bi-annual | In Progress